## Backlog-Android-S1
Mint Medical - Project Backlog
start date: | 2014-06-09 |  | Current completition rate (%) | 0%
full version app test | 2014-07-07 |  | Time left (days) | 51
Bug & crashes | 2 weeks
Date Complete | 2014-07-21
Curent priority | Previous Priority | Features | Function description | Bug Pictures | Original estimate (Hr) | Sprint estimate (Day) | Curent estimate (Day) | Scheduled sprint (Current plan) | Actual Sprint | Risk rating | In testing? | Done?
1 |  | Introduction Screen (S1) | 1. Slides right/left to see next/previous introduction slides 2. Click Done on last slide > Go to Home Screen (S2) |  | 8 | [5 empty] | Not yet
2 |  | Home Screen (S2) | 1. Appointment - This allow users to actively find and book appointment with registered Doctors - Number of booked appointments are shown in small line under - When tapped > Go to Appointment Screen (S4) 2. Treat me now - Allow user to describe his issues and submit information to Mint Medical Admin - When tapped > Go to Treat Me Now Screen (S5) |  | 8 | [5 empty] | Not yet
3 |  | Home Screen (S2) | 3. Prescription - Show user’s prescriptions that he is following - When tapped > Go to Prescription Screen (S6) 4. Locations - Show location nearby user on List-view or Map-view - When tapped > Go to Location Screen (S7) |  | 8 | [5 empty] | Not yet
4 |  | Home Screen (S2) | 5. Contact: When tapped > Go to Contact Screen (S8) 6. My Account: When tapped > Go to My Account Screen (S9) |  | 8 | [5 empty] | Not yet
4 |  | Home Screen (S2) | 8. Login: When tapped > Go to Login Screen (S3). - When user already logged in > Show Log Out. When tapped on Log-out > Go to Introduction Screen (S1) |  | 4 | [5 empty] | Not yet
5 |  | Login Screen (S3) | 1) Login by registered email and password - After fulfill information & tap on Login > Go to Home Screen (S2) with “Log-out” word on Top right 2) Click Register (for user who not yet have account) - When tapped > Go to Server Register site (Se1) 3) Tap on Forget password > Go to Server Forget password site (Se2) 4) Click cancel to come back Home Screen (S2) with “Log-in” word on Top right |  | 8 | [5 empty] | Not yet
6 |  | Appointment Screen (S4) | 1. Back - When tapped > Go back to Home Screen (S2) 2. New - When tapped > Go to S4-A (To start making appointment) |  | 8 | [5 empty] | Not yet
7 |  | Appointment Screen (S4) | 3. New Appointment - In 1st time login, it says “you have no upcoming appointments” > start making appointment by tap on “New appointment” > Go to S4-A - After 1st appointment booked, this icon disappeared, and be replaced by list of Upcoming Appointment (As shown on S4-I) |  | 8 | [5 empty] | Not yet
8 |  | Appointment Screen (S4) | 4. Appointment History - In 1st time login, it says “You have no history appointments. Please start your first one by tap on “New Appointment” above” - When user made his appointment, the appointment history list will be shown on S4-I |  | 8 | [5 empty] | Not yet
9 |  | Appointment Screen (S4) | MORE DETAILS ABOUT APPOINTMENT SCREEN (Detailed of screen can be seen at S4-A to S4-I, requirement file) 1. At S4-A: User can choose appointment types. 1.1. When tap on “My primary care team” > Go to Visit type S4-B Screen > When choose any Visit type > Go to Reason screen S4-C Screen > After writing reason & tap “Next” > Go to Availability screen S4-D > Choose an appointment > Go to Details screen S4-E > Tap “Book Appointment” > Go to Se you soon screen S4-F |  | 16 | [5 empty] | Not yet
10 |  | Appointment Screen (S4) | 1.2. When tap on “A specific office” > Go to S4-B > Show a list of Office as S4-G screen > Choose an office > Go to S4-C > After writing reason & tap “Next” > Go to Availability screen S4-D with only available times of doctors at this office only (*)> Choose an appointment > Go to Details screen S4-E > Tap “Book Appointment” > Go to Se you soon screen S4-F |  | 16 | [5 empty] | Not yet
11 |  | Appointment Screen (S4) | 1.3. When tap on “A specific doctor” > Show a list of Doctor as S4-H > Choose a Doctor > Go to Visit type S4-B Screen > When choose any Visit type > Go to Reason screen S4-C Screen > After writing reason & tap “Next” > Go to Availability screen S4-D with only available time of that Doctor only > Choose an appointment > Go to Details screen S4-E > Tap “Book Appointment” > Go to Se you soon screen S4-F |  | 16 | [5 empty] | Not yet
12 |  | Treat Me Now Screen (S5) | This screen allow user to describe a short explanation of his issue Tap on Cancel > Go to Home screen (S2) Tap “Send request” icon > Go to S4-F with word change to “Your request is sent! Our team will contact you soon to help you.” => Then this request will sent to Control panel of Mint Medical Admin for further action |  | 16 | [5 empty] | Not yet
13 |  | Prescription Screen (S6) | 1. Prescription Request Status + View history request + Status of request 2. View prescription detail, from Doctor send & Admin Mint Medical send 3. Request new Prescription + Write in box + Send to Admin |  | 16 | [5 empty] | Not yet
14 |  | Locations Screen (S7) | There are 2 options to view 1. Click on List = View on list (The list be shown is the same with list on S4-G) * There are a background under “List” icon 2. Click on Map = View on map with the center point is Current location & office surrounding if they are close enough * There are a background under “Map’’ icon 3. When tap a location (Office) > Go to S7-A Screen |  | 12 | [5 empty] | Not yet
15 |  | Locations Screen (S7) | 1. Icon back > Go to Location screen (S7) 2. Map-view = appearance of office location of map 3. Office name & address is shown 4. Book an appointment: Tapped > Go to S4-B > S4-C > After writing reason & tap “Next” > Go to Availability screen S4-D with only available time of doctors on that office only > Choose an appointment > Go to Details screen S4-E > Tap “Book Appointment” > Go to Se you soon screen S4-F 5. Call this office: Tapped > Pop-up Phone app with Call action right away happen (user call to office) 6. Driving direction: Tapped > Show direction from current location to this location |  | 12 | [5 empty] | Not yet
16 |  | Contact us Screen (S8) | 1. My doctor - When user not yet buy membership > Can not see - When user bought membership > Appear for usage 2. One medical support: Tapped > Open Mail App with + Mail title = Support + To = admin@mintmedical.sg / admin@ilokun.com (client’s confirmation) 3. Feedback: Tapped > Open Mail App with + Mail title = Feebback + To = feedback@mintmedical.sg / feedback@ilokun.com (client’s confirmation) 4. Share: Tapped > Open Mail App with + Mail title = Mint Medical Service – Register yours + From = client’s email address + Content = (client’s confirmation) |  | 8 | [5 empty] | Not yet
17 |  | Account Screen (S9) | 1. User's information when registered appear here + Picture + Name + Joining year + Email address & Contact 2. Click on update my account > Go to Web view to update & make payment if user want to |  | 4 | [5 empty] | Not yet
18 |  | About Mint Medical Screen (S10) | 1. Content to be provided by client 2. What we offer: Tapped > Go to detail screen. Content to be provided by client 3. Location: Tapped > Go to Location screen (S7) |  | 8 | [5 empty] | Not yet
19 |  | Map 2.3 |  |  | 12

## Backlog-Server-S1
Mint Medical - Project Backlog
Start date on 3 Jun 2014 => 1st full version app test on 1 Jul 2014 => Bugs & crashes fix in 2 weeks => Date of completition: 15th Jul 2014
|  |  | Current completition rate (%) | 0%
|  |  | Time left (days) | 48
Curent priority | Previous Priority | Features | Function description | Bug Pictures | Original estimate (Hr) | Sprint estimate (Day) | Curent estimate (Day) | Scheduled sprint (Current plan) | Actual Sprint | Risk rating | In testing? | Done?
1 |  | Admin Control Panel | 1. Create clinic location + Name of office/clinic location + Address + Zip-code + Contact + Longitude, Latitude |  | estimate here | [5 empty] | Not yet
2 |  | Admin Control Panel | 2. Create Doctor profile + Name + Doctor level/Professional + Contact/phone no + At name of office/clinic location + Picture |  | estimate here | [5 empty] | Not yet
3 |  | Admin Control Panel | 3. Treat me now request + View list of request sent to server + Name, patient ID + Prescription detail + Time of request |  | estimate here | [5 empty] | Not yet
4 |  | Admin Control Panel | 4. Doctor available view + View list + Search for name + View doctor time management |  | estimate here | [5 empty] | Not yet
5 |  | Doctor Control Panel | 1. Create available time for patient booking + Date & Time |  | estimate here | [5 empty] | Not yet
6 |  | Doctor Control Panel | 2. View appointment detail from Patient + Patient’s information + Type of visit + Reason |  | estimate here | [5 empty] | Not yet
7 |  | Doctor Control Panel | 3. Input prescription for Patient & send + Input text and send |  | estimate here | [5 empty] | Not yet
8 |  | Register screen | 1. Require information: + First & Last name + Gender + DOB + Email address & confirm + Password & Confirm 2. Activation email via Mail |  | estimate here | [5 empty] | Not yet
9 |  | Payment via Paypal | Paypal intergration |  | estimate here | [5 empty] | Not yet

## Testers
Testers
Tuyển Dào
zhuge.dao11@gmail.com
9bea1ec9bf180b2fae8ee6ca9f77ea0079fdad3e